Agile Workshop

Creating The Project Plan and Sprint Backlog for Your Group Project

Part 1: Understand The Case Study

Read the full case study as a group. Your first task is to understand the business problem before creating technical tasks.

Discuss and record:

- What organisation or business context is described?

Organizational/Operational Context: A hospital requires unified management of patient referrals, outpatient appointments, treatment and chemotherapy scheduling, payment and refund processing, clinical correspondence, and patient inquiries. Various clinical, administrative, and financial departments, as well as external entities, need to securely exchange information.

- Who are the main stakeholders?

Patients; referring institutions or General Practitioners (GPs); medical secretaries; consultant physicians; outpatient appointment teams; treatment and chemotherapy appointment teams; clinical specialist nurses; telephone consultation teams; finance teams; patient pathway coordinators; administrative staff; and external service providers

- What is the main business process?

Receive referral → Collect examination materials → Consultant physician review → Arrange outpatient visit → Obtain consent for diagnosis and treatment → Authorize treatment request → Confirm funding or payment → Arrange treatment/chemotherapy → Follow-up, correspondence, and ongoing management

- What problem is the proposed system trying to solve?

Establish traceable patient pathways to reduce information loss, unauthorized access, duplicate appointments, and duplicate billing, while enhancing cross-departmental collaboration, anomaly handling, access control, and auditing.

- What are the key business rules?

- What exceptions or alternative paths are described?

Incomplete documentation, referral rejection, request for additional information, referral to another specialty, unavailable appointment time, patient cancellation or failure to attend, failed external service, unapproved funding, failed or unconfirmed payment, treatment delay or modification, failed refund request, and delayed clinical correspondence

- What external systems or organisations are involved?

- What information must be captured, stored, transferred or validated?

Patient identity and contact information; referral materials; clinical decisions; appointment and contact records; consent and treatment authorization; examination results; payment and refund records; clinical correspondence; query status; and audit data such as user, date, time, and operation type.

Task 1: Case Study Summary

Create a short group summary of the case study.

Your summary should include:

Main business process.

Main participants.

Key requirements.

Important business rules.

External services or organisations.

Assumptions made by the group.

The complete care pathway encompasses the entire process—from the patient's referral to the hospital through clinical review, outpatient appointment scheduling, diagnosis, treatment authorization, confirmation of funding or payment, treatment administration, to subsequent patient management. Key participants include the patient, the referring institution, the medical secretary, the consulting physician, the appointment and treatment team, nurses, the finance team, the patient pathway coordinator, administrative staff, and various external service providers.

Part 2: Identify The Main Deliverables

Task 1: Create a list of deliverables.

| Deliverable | Related Requirement(s) | Dependencies | Due Date | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Case Summary and Requirements List | R01-R13; BR01-BR12 | Case Study Materials | First phase completed | Comprehensive coverage of participants, processes, rules, exceptions, and assumptions |
| Operational Layer – BPMN | A01; R01-R13 | Requirements List | Second phase concluded | Submit the.bpmn file and a clear PDF; responsibilities, messages, branches, and exceptions must be fully documented. |
| Executable Camunda BPMN | A01; R01-R13 | Operational Layer – BPMN | Phase II – First Edition; Phase IV – Revised Edition | Deploy and demonstrate according to the confirmed scope; record versions and limitations. |
| Camunda Form | R01-R05; R08 | Data and Role Definitions | Second phase concluded | Key fields, mandatory validation, and permission compliance with the established workflow |
| External Service Prototype | R02; R04-R07; R11 | API Specification | Phase II: Prototype; Phase IV: Improvement and Validation | Display success, failure, and safe retry; indicate the simulated interface. |
| Acceptance Testing Plan | A02; R01-R13 | Requirements; Operational Layer – BPMN | Second phase concluded | Standardized correlation requirements; comprehensive coverage of scenarios, data, steps, and decision rules |
| Demonstration and Decision-Making Justification | A03; A01-A02 | Reviewed initial model and test plan | Second phase concluded | Includes operational models, test plans, decision-making, and alternative approaches |
| Strategic Level – BPMN | A04 | initial version | Phase III: Initial Draft; Phase IV: Final Version | The business layer model is mapped to the initial operational model; provides source files and PDFs. |
| i* SD and SR Models | A05 | Initial version; Stakeholder Objectives | Phase III: Initial Draft; Phase IV: Final Version | SD and SR are consistent; provides editable source files and readable PDFs. |
| Requirement Consistency Assessment | A06 | Strategic layer: BPMN; SD/SR; Traceability Relationships | Phase IV has concluded. | Traceability support, partial support, and unsupported requirements – propose improvements. |
| Acceptance Assessment | A07 | Baseline standard; specified version; Testing | Phase IV has concluded. | Retain the original and revised standards, actual results, and evidence of failure. |
| Agile activities and contribution evidence | A08 | Current Task Board and Warehouse | Continuous recording at each stage; archiving at the end of each stage. | Save personal progress, review snapshots, feedback, retrospectives, and handovers |

Part 3: Create The Product Backlog

The product backlog is the full list of work required for the project. It should include modelling, implementation, testing, review and evidence tasks.

Create backlog items based on the case study provided.

Each backlog item should include:

- Backlog ID.

- Task title.

- Description.

- Priority.

- Related requirement or business rule.

- Estimate.

- First owner.

- Second owner.

- Dependencies.

- Acceptance conditions.

- Evidence required.

- Status.

| ID | Backlog Item | Description | Priority | Related Requirement | Estimate | First Owner | Second Owner | Dependencies | Acceptance Conditions | Evidence | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PB01 | Requirements and Assumptions | Sorting out needs, rules, and questions | High | R01-R13 | 3 | Xinran Zhang | Cathleen | NONE | Needs and assumptions are traceable | Rule records | Done |
| PB02 | Operational Layer Main Process | Connect referrals to follow-up processes | High | A01; R01-R13 | 5 | Cathleen | Xinran Zhang | PB01 | Characters, boundaries, and main storylines are clear | BPMN | Planned |
| PB03 | Referral Review | Four types of decisions and supplementary materials | High | R01; BR01 | 5 | Xinran Zhang | cyc | PB01-02 | Appointments cannot be made before receiving referrals | BPMN; AC01 | Planned |
| PB04 | Book an appointment and contact the patient | Appointments, notifications, and rescheduling | High | R02; R09 | 7 | Cathleen | cyc | PB03 | Rules BR02 and BR11 are complete | Form；AC02／11 | Planned |
| PB05 | Treatment Authorization | Patient consent and clinical authorization | High | R03; BR03 | 3 | Xinran Zhang | Churchill | PB02 | Unauthorized requests cannot be processed | Form；AC03 | Planned |
| PB06 | Funding, Payment and Refund | Grant confirmation, reconciliation, and refund | High | R04; R06 | 7 | Cathleen | Xinran Zhang | PB05 | Rules BR04–BR06 are complete | AC04-06 | Planned |
| PB07 | Treatment and chemotherapy | Periodic reviews and authorization changes | High | R05; BR07 | 5 | Xinran Zhang | Cathleen | PB05-06 | Clinical and administrative decisions are separated | AC07 | Planned |
| PB08 | Outpatient correspondence | Approval, sending, and reminders | Low | R07; BR08-BR09 | 3 | cyc | Xinran Zhang | PB02 | Complete seven-day and graded follow-up | AC08 | Planned |
| PB09 | Patient consultation | Classification, diversion, and closure | Low | R08; BR10 | 3 | cyc | Churchill | PB01 | Record responsibilities and handling outcomes | AC09 | Planned |
| PB10 | Authority and audit | Character boundaries and operation records | High | R10; BR12 | 3 | Cathleen | Churchill | PB01; PB02 | Rejecting overreach; Protecting audits | AC10 | Planned |
| PB11 | Acceptance test plan | Scenarios, data, and judgment rules | High | A02; R01-R13 | 7 | Churchill | Cathleen | PB01 | AC01–AC13 fields are complete | Test the plan | Planned |
| PB12 | Version integration and validation | Save baselines and integrate improvements | High | A01; A07 | 7 | Churchill | cyc | T18 ，T33 | Versions, changes, and evidence associations | Test the plan | Planned |
| PB13 | Reports and accessibility | Indicator sources and communication preferences | Low | R12-R13 | 3 | cyc | Churchill | PB01; PB04; PB09 | Indicators and preferences are sourced from data | Data/report mapping | Planned |
| PB14 | Strategic layer BPMN | Sort out the responsibilities and interactions at the business level | Low | A04 | 5 | Cathleen | Xinran Zhang | T18 | Strategic activity mapping initial version | BPMN; PDF | Planned |
| PB15 | i* Model and Model Improvement | Establishing SD/SR; Revising three types of models | Low | A05 | 7 | Churchill | Xinran Zhang | Modeling: T18 Refinement: T24–T27 | Model consistency; Feedback has been handled | Source file; PDF | Planned |
| PB16 | Demand consistency assessment | Trace objectives and identify gaps | Low | A06 | 7 | Xinran Zhang | cyc | T27 | Gaps correspond to improvement actions | Matrix; Evaluation | Planned |
| PB17 | Acceptance execution and evaluation | Implement, revise standards, and re-test | Low | A07 | 7 | Churchill | Cathleen | T29, T32, T34 | Actual results and standards are well documented | Testing; Evaluation | Planned |
| PB18 | Demonstration and decision argumentation | Explain the model, testing, and trade-offs | High | A03 | 3 | cyc | Churchill | PB11; PB12 | Includes models, plans, and arguments | slides; decision records | Planned |
| PB19 | Agile documentation and handoffs | Stand-up meetings, reviews, feedback, and reviews | High | A08 | 7 | Xinran Zhang | Churchill | PB01 | Each round record is verifiable | slides; decision records | Planned |
| PB20 | External interfaces and recovery | Request, failure, retry, and re-admission | High | R02; R04; R10-R11 | 7 | Churchill | Cathleen | PB01; PB02 | Recovery should not be repeated or patient combined | interface agreement; log | Planned |

Part 4: Break The Work into Project Tasks

Each backlog item should be broken into manageable tasks. A task should be small enough to track and complete within a sprint.

Avoid large tasks such as:

- “Do BPMN”

- “Create system”

- “Do testing”

- “Make presentation”

Use specific tasks such as:

- Identify process participants.

- Draft main BPMN flow.

- Add exception path for rejected request.

- Create Camunda Form for referral submission.

- Implement external worker for validation.

- Test normal workflow path.

- Record feedback response.

| Task ID | Backlog ID | Task Description | First Owner | Second Owner | Estimate | Dependency | Acceptance Conditions | Evidence Required | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T01 | PB01 | Extract functional requirements and assign numbers | Xinran Zhang | Cathleen | 3 | None | R01–R13 correspond to case content with traceable sources | Requirements list and case corresponding records | finish |
| T02 | PB01 | Record business rules, exceptions, and assumptions | Xinran Zhang | Cathleen | 3 | T01 | BR01–BR12 Clearly described; Items to be confirmed are listed separately | Business rules and a list of assumptions | Planned |
| T03 | PB02 | Define participants and map the main patient flow | Cathleen | Xinran Zhang | 5 | T01; T02 | Clear role boundaries; Complete transition from referral, appointment, treatment, to follow-up | Main flow BPMN and swimlane | Planned |
| T04 | PB03 | Completion of referral review and document supplementation pathways | Xinran Zhang | cyc | 5 | T03 | Acceptance, refusal, supplementary documents, and complete transfer pathways to specialists; No appointment is accepted before acceptance | Review BPMN；AC01 | Planned |
| T05 | PB04 | Create appointment forms and patient contact procedures | Cathleen | cyc | 5 | T04 | Record time periods and special needs; For appointments within the next 14 days, contact by phone according to the rules and leave a trace | Appointment form; Contact records; AC02 | Planned |
| T06 | PB04 | Supplement abnormal follow-up and appointment paths | Cathleen | cyc | 3 | T05 | There are procedures for cancellations, absenteeism, and unsuitable time slots, and relevant personnel are notified | Abnormal BPMN; AC11 | Planned |
| T07 | PB05 | Create patient consent and treatment authorization forms | Xinran Zhang | Churchill | 3 | T03 | Administrative processing will only proceed after consent, authorization, and all required documents are completed | Camunda Form;AC03 | Planned |
| T08 | PB06 | Establish pathways for funding, payment, and missing confirmation processing | Cathleen | Xinran Zhang | 7 | T07 | Covers funding, self-funding, exemptions, and failures; Verify deficiencies first to avoid duplicate charges | Payment BPMN；AC04–AC05 | Planned |
| T09 | PB06 | Add full and partial refund approval paths | Cathleen | Xinran Zhang | 3 | T08 | Refunds are authorized by the finance, and the refund result is linked to the original transaction | Refunds are given BPMN；AC06 | Planned |
| T10 | PB07 | Complete cycle examinations and treatment changes pathways | Xinran Zhang | Cathleen | 5 | T07 | Clinical staff decide to continue, postpone, or change the contract; Retain authorization and emergency supplementary enrollment, and transfer to finance when expenses are involved | Treatment BPMN；AC07 | Planned |
| T11 | PB08 | Arrange outpatient letter approval, reminders, and reporting | cyc | Xinran Zhang | 3 | T03 | Covers seven-day, weekly, one-month, and three-month rules; Stops reminders after completion | Letter BPMN；AC08 | Planned |
| T12 | PB09 | Establish consultation classification, transfer, and closure processes | cyc | Churchill | 3 | T03 | Clinical, financial, and administrative consultations are transferred to the relevant personnel; Record the handling results | Consultation BPMN；AC09 | Planned |
| T13 | PB10 | Define role permissions and critical operation audits | Cathleen | Churchill | 3 | T02; T03 | Rejection of unauthorized clinical or financial operations; Traceability of key modifications | Permission Matrix; Audit Sample; AC10 | Planned |
| T14 | PB11 | Prepare and review the acceptance test plan | Churchill | Cathleen | 7 | T04–T13; T17; T27 | AC01–AC13 include data, steps, expectations, and decision rules; Requirements and anomalies are covered and traceable | test plan; coverage checklist | Planned |
| T15 | PB12 | Integrate the initial version and check the main workflow | Churchill | cyc | 3 | T04–T14; T17; T27 | The main workflow can run within the agreed scope; Save versions, operation instructions, and problem lists | Initial version snapshot; running log | Planned |
| T16 | PB12 | Integration of confirmed second version improvements | Churchill | cyc | 5 | T22; T23 | Select improvements that have been merged; Change related requirements or test issues; Retain the initial version | Second version of the document; Change History | Planned |
| T17 | PB13 | Define management reports and communication preference fields | cyc | Churchill | 3 | T02; T05; T12 | R12 Indicators have data sources; R13 Communication and accessibility require recording fields | Field Mapping; AC13 | Planned |
| T18 | PB14 | Strategy drawn according to the initial version of BPMN | Cathleen | Xinran Zhang | 5 | T15 | Clear business responsibilities and external interactions; Strategic activities correspond to initial operational processes | Strategic BPMN source file and PDF | Planned |
| T19 | PB15 | Creating the i* Strategic Dependency Model (SD) | Churchill | Xinran Zhang | 3 | T15; T02 | Clarify participants and objectives, tasks, resources, and soft goal dependencies | SD source file and PDF | Planned |
| T20 | PB15 | Creating the i* Strategic Rationale Model (SR) | Churchill | Xinran Zhang | 5 | T19 | Internal goals and task relationships are clear; Terminology aligns with SD | SR source files and PDFs | Planned |
| T21 | PB15 | Creating the i* Strategic Rationale Model (SR) | Churchill | Xinran Zhang | 5 | T18–T20; T22 | Feedback is recorded for processing; Terminology, relationships, and versions of the three types of models are consistent | Revise the model; Feedback handling records | Planned |
| T22 | PB16 | Build a traceability matrix and assess demand consistency | Xinran Zhang | cyc | 9 | T18–T20 | Distinguish supported, partially supported, and unsupported; Gap corresponds to model basis and improvement actions | traceability matrix; consistency assessment | Planned |
| T23 | PB17 | Perform baseline acceptance testing for the initial version | Churchill | Cathleen | 5 | T14; T15 | Actual results are associated with the version; Evidence of passing, failing, and issues is fully preserved | Test execution records; Screenshots or logs | Planned |
| T24 | PB17 | Revised acceptance standards and retested the improved version | Churchill | Cathleen | 7 | T16; T21; T23 | Explain the reason for the standard revision; Retain the original results and separately report the retest results of the original and new standards | Acceptance evaluation; Retest records; Evidence index | Planned |
| T25 | PB18 | Organize presentation materials and design decision basis | cyc | Churchill | 3 | T14; T15 | Including operating models, test plans, and design trade-offs; Members can explain their own decisions | Presentations; Decision records | Planned |
| T26 | PB19 | Record the stand-up meetings, evaluations, and handovers at each stage | Xinran Zhang | Churchill | 7 | T01； | Each stage is spent 2 hours recording SU/SR, individual contributions, feedback, and handovers; Acceptance at each stage | Four-stage meetings and contribution records | Planned |
| T27 | PB20 | Define interfaces and verify failures, retry, and recovery | Churchill | Cathleen | 7 | T02; T03 | Interface fields, errors, and recovery rules are clearly defined; Retries do not involve duplicate appointments or fees, and patient confusion is avoided | interface contract; code; log recovery; AC12 | Planned |

Part 5: Dependency Mapping

For each task, identify:

- What must be completed first?

- Which task depends on this task?

- Who needs to be informed if this task is delayed?

- What is the backup plan?

Part 6: Create Sprint Backlogs

Select tasks from the product backlog for each sprint.

| Sprint | Task ID | Task Description | First Owner | Second Owner | Estimate | Acceptance Conditions | Evidence | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T01 | Confirm the requirements baseline | Xinran Zhang | Cathleen | 3 | None | Requirements R01-R13 link to case evidence. | Requirements register | Done |
| T02 | Record rules, exceptions and assumptions | Xinran Zhang | Cathleen | 3 | T01 | BR01-BR12 and unresolved questions are recorded. | Rules and assumptions | Planned |
| T03 | Model actors and the main patient pathway | Cathleen | Xinran Zhang | 5 | T01; T02 | Roles and referral-to-follow-up flow are clear. | Initial BPMN | Planned |
| T04 | Model referral review and missing information | Xinran Zhang | cyc | 5 | T03 | Four review outcomes; booking follows authorised acceptance. | Referral BPMN; AC01 | Planned |
| T05 | Create booking and contact procedures | Cathleen | cyc | 5 | T04 | Record booking needs and telephone attempts for appointments within 14 days. | Form; AC02 | Planned |
| T07 | Create consent and treatment authorisation forms | Xinran Zhang | Churchill | 3 | T03 | Administrative processing requires a complete, authorised request and consent. | Forms; AC03 | Planned |
| T12 | Model enquiry routing and closure | cyc | Churchill | 3 | T03 | Enquiries are classified, assigned and resolved by the appropriate team. | Enquiry BPMN; AC09 | Planned |
| T13 | Define permissions and audit requirements | Cathleen | Churchill | 3 | T02; T03 | Unauthorised actions are rejected; significant actions are traceable. | Role matrix; AC10 | Planned |

Part 7: Prepare For Standups

Your group must be ready to provide individual standup updates.

Each student should prepare:

- What I completed.

- What I will do next.

- What is blocking me.

- What evidence supports my update.

- Whether I need second-owner support.

- Whether any handover is required.

| Student | Completed Work | Evidence | Next Action | Blocker | Support Needed | Handover Required |
| --- | --- | --- | --- | --- | --- | --- |

Part 8: Prepare For Sprint Reviews

At each sprint review, the group must demonstrate the current integrated increment.

You should be ready to show:

- Completed tasks.

- Unfinished tasks.

- Key decisions.

- Evidence of integration.

- Testing or validation evidence.

- Feedback received.

- Backlog updates.